## Sheet1
React Native Training Tracker
Item | Completion Date (est.)
TypeScript; Transform Login, and Dashboard Screen in TypeScript | COB 20th July | Login, Pin, Dashboard Screens converted to typescript
Apollo GraphQL and GraphQL Queries; Optimize GraphQL queries and Apollo implementation | 27th July (21th July is half day for me) | Refactored Queries
Flexbox | COB 28th July
Tabs, and Drawers in React Native Add Bottom Tab and show Drawer along with Flexbox (will add empty screens for each tab) |  | Implemented Material Bottom Tabs with Simple Stack Navigator. Didn’t find a way to use drawer and tab navigator from the App file. Intention was to use of them together, the only viable solution was to add either one as global and other one at the class level. This latter approach makes better sense.
Flat List with pagination; Will add content to Jobs Screen with pagination | COB 3rd August COB 4th August (half day) | Implemented Flatlist with pagination sourcing data from an api. Pagination: Whenever there is more data to show then the visible space then pagination function helps query the api or source to fetch next set of data. Meaning the source is queried again with the last visible item's reference and new data is appended with existing visible data.
UI Animations; Will add Splash Screen with Animations | COB 10th August | The Animated API comes bundled with React by default. There are a couple of functions to show the animations on the screen. The most useful one is Animated.timing; it gives the most control. Most of the animations can be done by using it. You need to provide duration and easing (predefined animations). Animated.spring: Provides a spring physics model. There few options combination to make the animation look good. Animated.decay: Has specific use cases, good for user interaction, momentum-based sliders. Animations are expensive in React native, therefore they need to be limited to splash screens or short animations. Specifically, users shouldn't be allowed to run the animations as they might end up running them multiple times.
Pure TypeScript Project | COB 11th Aug | Created Expo TypeScript project with redux reducer. Tsconfig strict mode enabled, types are enforced. When types are enforced its often difficult to find the right type of the object.
Redux (I know persist, but there are other components as well like thunk, saga, etc.) ; I have to look how can I used them in the project, will give estimate later. | COB 18th Aug | Added on top of the typescript project. Middleware: Middleware in React provides extension point betweeb dispatching action, and the moment it reaches the reducer. Furthermore, with different options of middlewares, async support is also provided. Redux-thunk: extends ability of redux store to write async logic which interacts with the store. In addition, redux-thunk returns a function instead of the action. Redux-saga: same like thunk, it extends ability of the redux store to write async logic which interacts with the store. Sagas can be controlled from the main application unlike thunk. Sagas utilizes ES6 feature generators which can be exited and re-entered, meaning sequential execution. There are no callback hell (passing in a function and using them inside). Sagas are advance middleware than thunk. They are easier to test.
Firebase | COB 24th August | User login authentication Email and password with firebase auth. Login inputs are made as a component which are further used to create a loginform. Then this loginform in imported to Login Screen with props. Firebase SignIn method is used async through Redux-Thunk.
Push Notifications; | COB 25th Auguest | Used Push Notifications with Firebase and Expo Push Notifications. Triggering Notification by listening to the Firebase Real Time Database. Expo internally manages the Native code for AndroidManifest, etc. Custom Push notification configuration is only available with React Native CLI.
Maps with Orientation | COB 1st September | React Native uses google's support on maps. Orientation in react native (expo app) utilizes DeviceMotion; from expo-sensors which provides device motion and orientation sensors, ScreenOrientation: gives orientation in which graphics are painted on the device. React Native apps can have a better orientation detection.
Native Modules
native-camera | 7th September | Implemented Camera module using react api for android. Super usefeul when a custom functionality is required on capture with camera on native device.
native-device-info | 8th September | requesting device information from android.
native-geolocation | 9th September | fetching geolocation using android fused location api and then returning as a promise.
native-share | 10th September | Had issue naming module as ShareModule it was colliding with com.facebook.react.share.ShareModule. To resolve it I overrid canOverrideExistingModule method to return true.
native-image-picker | 11th September | Accessing Gallery using Native Android Module. With Bare App all permissions and services are required to be managed, unlike in expo where its handled by expo itself.
Native Orientation Change, UI Changes on orientation change and LifecycleEvents | 15th September | Often user rotate their device to have a better viewing, for this its essential that orientation changes are handled.
native-video | 21st September | Native videoview added with default mediacontroller. Added and accessing this videoview native ui component from front-end React Native code. This connection allows us to build media controller at the RN end that can work for both naitve platforms.
native-vide with RN controls | 23rd September | Added media control at the RN end with blank native videoview. This helps us create a customise media controller that can control both native platform video play backs. This gluing of both native ui component and RN component is done through the RN bridging library. By using this bridging RN acts as client and native code as server. RN bridging api provide few pre-configured event handling like 'onClick', 'onLoadingFinish', 'onLoadingStart', etc on native ui component which can be listened by the RN component and further process it. In addition, the bridging api also allows to create your own custom events which needs to be registered at the native side, and then listened by RN component. Surely very helpful in creating custom ui component events. The process for other views would be simple as well.
NPM Packages
React-native-camera | 23rd September | React native camera provides ability to scan barcodes, take pictures, and submit picture to cloud for machine learning. (Firebase supported)
React-native-device-info | 23rd September | Didnt install, it should be simple. I am already natively fetching device information.
React-native-geolocation | 24th September | It provides react native app to fetch user's user location using robust api. Instead of writing native code to fetch the same information this geolocation package does everything for you.
React-native-share | 24th September | Simple package to help share data to external app using react native.
React-native-cameraroll / react-native-image-picker | 25th September | CameraRoll is comprehensive api package that helps fetch, and delete media files (images, videos). Image-picker provides help to select images using photo gallery or Camera. (primary for iOS, but supports Android also)
zIndex | 25th September | Experimented zIndex in flexbox to overlap scrollview on another parent view.
React-native-video | 28th September
React Navigation 5.1
Bare App/Expo Pros/Cons
TypeScript/JavaScript
Redux/React Context
Payment Processing
JEST Testing 1. Basic Testing (non-react) 2. Redux Testing 3. Mocking 4. Snapshots | couldn’t complete the list, will have to come back later to this. Blocked due to the TypeScript usage. Try to use jest going forward.